## Data input
Gantt chart for joint appointment procedures in Berlin
This Gantt chart is for planning joint appointment procedures. It is based on the results of a working group on speeding up joint appointment procedures involving representatives of Freie Universität Berlin, Humboldt-Universität zu Berlin, Technische Universität Berlin and the Leibniz Association, which summarised idealised and generalised procedural steps for joint appointment procedures between September 2018 and February 2019.
The following data can be entered to minimise the time taken and optimise the procedure:
Mandatory field
Procedure to be completed on: | 2022-06-01 | Procedure should start before 06.01.2021
Optional fields for dates (in chronological order) | Date | Comment
Joint preliminary discussion |  | Appointment should be before 27.01.2021
Meeting of the institute board (establish purpose, set up appointment committee, etc.) |  | Appointment should be before 24.03.2021
Meeting of the faculty board (establish purpose, set up appointment committee, etc.) |  | Appointment should be before 07.04.2021
Meeting of the academic senate |  | Appointment should be before 28.04.2021
Meeting of the Executive Board |  | Appointment should be before 05.05.2021
Constitutive meeting of the appointment committee |  | Appointment should be before 28.07.2021
Second meeting of the appointment committee (interviews with applicants) |  | Appointment should be before 25.08.2021
Third meeting of the appointment committee (shortlist; report) |  | Appointment should be before 01.12.2021
Meeting of the Scientific Advisory Board of the Leibniz institute (shortlist) |  | Appointment should be before 29.12.2021
Meeting of the institute committee of the Leibniz institute (shortlist) |  | Appointment should be before 12.01.2022
Meeting of the Board of the Leibniz institute (shortlist) |  | Appointment should be before 19.01.2022
Meeting of the faculty board (shortlist) |  | Appointment should be before 22.12.2021
Meeting of the academic senate (shortlist) |  | Appointment should be before 12.01.2022
Meeting of the Executive Board (shortlist) |  | Appointment should be before 19.01.2022
Note:
To display the Gantt chart correctly in days, the start and end dates of the process must be entered in the axis options.
Does not take account of annual leave/public holidays, etc.
For questions and comments, please contact: info@leibniz-gemeinschaft.de

## Detailed calculation
Detailed process overview | [5 empty] | Key:
It is possible to modify the individual process steps by adjusting the duration. | [5 empty] | N := Non-university research institution
U := University
S := Berlin Senate
The table can be modified by adjusting the duration in weeks | [5 empty] | Combinations (NU, NUS) mean several institutions are responsible
The links are protected so that the table will continue to function even if entries are incorrect | [5 empty] | Does not take account of annual leave/public holidays, etc.
Adjustments: | possible | possible | possible | not possible | not possible | not possible |  | not possible | not possible | not possible
Process steps | Duration | of which preparation | of which possible overlap | Duration | Total time since start | Start date | Hilfsdatum (später ausblenden) | End date | Fixed date (must be earlier than end date) | If an error message appears there is a scheduling conflict
Unit | Weeks | Weeks | Weeks | Days | Days | Date | Date | Date | Date
Start of the procedure | 0 |  |  | 0 | 0 | 2021-01-06 | 2021-01-06 | 2021-01-06 |  | TRUE
N: Expression of interest | 1 |  |  | 7 | 0 | 2021-01-06 | 2021-01-06 | 2021-01-13 |  | TRUE
UN: Joint discussion | 2 |  |  | 14 | 7 | 2021-01-13 | 2021-01-13 | 2021-01-27
U: Consultation institute level | 2 |  |  | 14 | 21 | 2021-01-27 | 2021-01-27 | 2021-02-10 |  | TRUE
U: Applications; drafts; scouting | 4 |  |  | 28 | 35 | 2021-02-10 | 2021-02-10 | 2021-03-10 |  | TRUE
U: Institute board | 2 | 2 |  | 14 | 63 | 2021-03-10 | 2021-03-10 | 2021-03-24
U: Faculty board | 2 | 2 |  | 14 | 77 | 2021-03-24 | 2021-03-24 | 2021-04-07
U: If appl. academic senate | 3 | 2 |  | 21 | 91 | 2021-04-07 | 2021-04-07 | 2021-04-28
U: If appl. President’s office | 3 |  | 1 | 21 | 91 | 2021-04-07 | 2021-04-14 | 2021-04-28 |  | TRUE
U: Executive Board | 2 | 1 | 1 | 14 | 105 | 2021-04-21 | 2021-04-28 | 2021-05-05
U: If appl. Board of Trustees | 4 | 2 |  | 28 | 119 | 2021-05-05 | 2021-05-05 | 2021-06-02 |  | TRUE
S: Establish agreement | 4 |  |  | 28 | 147 | 2021-06-02 | 2021-06-02 | 2021-06-30 |  | TRUE
U: Prep. advertisement | 4 |  | 4 | 28 | 147 | 2021-06-02 | 2021-06-30 | 2021-06-30 |  | TRUE
U: Publication | 4 |  |  | 28 | 175 | 2021-06-30 | 2021-06-30 | 2021-07-28 |  | TRUE
UN: Const. and 1st AC | 4 | 4 | 4 | 28 | 175 | 2021-06-30 | 2021-07-28 | 2021-07-28
UN: Assess applications | 2 |  |  | 14 | 203 | 2021-07-28 | 2021-07-28 | 2021-08-11 |  | TRUE
UN: Interviews 2nd AC | 4 | 2 | 2 | 28 | 203 | 2021-07-28 | 2021-08-11 | 2021-08-25
UN: Request external reviews | 10 | 2 |  | 70 | 231 | 2021-08-25 | 2021-08-25 | 2021-11-03 |  | TRUE
UN: 3rd AC: Shortlist, report | 4 |  |  | 28 | 301 | 2021-11-03 | 2021-11-03 | 2021-12-01
N: Scientific Adv. Board | 4 | 4 |  | 28 | 329 | 2021-12-01 | 2021-12-01 | 2021-12-29
N: Institute committee | 2 | 2 |  | 14 | 357 | 2021-12-29 | 2021-12-29 | 2022-01-12
N: Board | 1 | 1 |  | 7 | 371 | 2022-01-12 | 2022-01-12 | 2022-01-19
U: Faculty board | 2 | 2 |  | 14 | 336 | 2021-12-08 | 2021-12-08 | 2021-12-22
U: If appl. academic senate | 3 | 2 |  | 21 | 350 | 2021-12-22 | 2021-12-22 | 2022-01-12
U: If appl. President’s office | 3 |  |  | 21 | 350 | 2021-12-22 | 2021-12-22 | 2022-01-12 |  | TRUE
U: Executive Board | 2 | 2 | 1 | 14 | 364 | 2022-01-05 | 2022-01-12 | 2022-01-19
S: Provisional offer (Ruferteilung) | 4 |  |  | 28 | 378 | 2022-01-19 | 2022-01-19 | 2022-02-16 |  | TRUE
N: Negotiations | 1 |  |  | 7 | 406 | 2022-02-16 | 2022-02-16 | 2022-02-23 |  | TRUE
UNS: Agreement on pay | 4 |  |  | 28 | 413 | 2022-02-23 | 2022-02-23 | 2022-03-23 |  | TRUE
U: If appl. negotiations | 4 | 4 | 2 | 28 | 427 | 2022-03-09 | 2022-03-23 | 2022-04-06 |  | TRUE
UN: Offer | 1 |  |  | 7 | 455 | 2022-04-06 | 2022-04-06 | 2022-04-13 |  | TRUE
UN: Candidate response | 4 |  |  | 28 | 462 | 2022-04-13 | 2022-04-13 | 2022-05-11 |  | TRUE
UN: Medical examination | 6 | 4 | 4 | 42 | 462 | 2022-04-13 | 2022-05-11 | 2022-05-25 |  | TRUE
Unit: N: Contract; Weeks: 1; Days: 7; Date: 2022-05-25; Date: 2022-06-01 | TRUE
Unit: Notes:; Date: Fixed dates for board/committee meetings can be entered | If the date does not fit with the target date for completing the appointment procedure, an error message will appear here

## Gantt in days
U: University
S: Berlin Senate
UN: University with non-university RI
UNS: University, non-university RI, Senate